## Slide 1: 6.3. What is a Lifecycle Model?
Definition.
A (software/system) lifecycle model is a
description of the sequence of activities
carried out in an SE project, and the
relative order of these activities.

## Slide 2
It provides a fixed generic framework that can be tailored to a specific project.
Project specific parameters will include:
Size, (person-years)
Budget,
Duration.
project plan =
lifecycle model + project parameters

## Slide 3
There are hundreds of different lifecycle models
to choose from, e.g:
waterfall,
code-and-fix
spiral
rapid prototyping
unified process (UP)
agile methods, extreme programming (XP)
COTS …
but many are minor variations on a smaller
number of basic models.

## Slide 4
By changing the lifecycle model, we can
improve and/or tradeoff:
Development speed (time to market)
Product quality
Project visibility
Administrative overhead
Risk exposure
Customer relations, etc, etc.

## Slide 5
Normally, a lifecycle model covers the entire
lifetime of a product.
From birth of a commercial idea
to final de-installation of last release
i.e. The three main phases:
design,
build,
maintain.

## Slide 6
Note that we can sometimes combine
lifecycle models,
e.g. waterfall inside evolutionary – onboard shuttle software
We can also change lifecycle model between releases as a product matures,
e.g. rapid prototyping  waterfall

## Slide 7
6.4. The Waterfall Model
The waterfall model is the classic lifecycle
model – it is widely known, understood
and (commonly?) used.
In some respect, waterfall is the ”common
sense” approach.
Introduced by Royce 1970.

## Slide 8
User Requirements
Software Requirements
Architecture Design
Detailed design & Coding
Testing
Delivery
The Waterfall
Lifecycle Workflow
Time
User Requirements Document
Software Requirements
Document
Architectural Design
Document
Detailed
Design
& Code
phase
output
”Swimming
upstream”

## Slide 9: Advantages
Easy to understand and implement.
Widely used and known (in theory!)
Reinforces good habits: define-before- design, design-before-code
Identifies deliverables and milestones
Document driven, URD, SRD, … etc. Published documentation standards, e.g. PSS-05.
Works well on mature products and weak teams.

## Slide 10: Disadvantages I
Idealised, doesn’t match reality well.
Doesn’t reflect iterative nature of exploratory development.
Unrealistic to expect accurate requirements so early in project
Software is delivered late in project, delays discovery of serious errors.

## Slide 11: Disadvantages II
5. Difficult to integrate risk management
Difficult and expensive to make changes
to documents, ”swimming upstream”.
Significant administrative overhead,
costly for small teams and projects.

## Slide 12: 6.5. Code-and-Fix
This model starts with an informal general
product idea and just develops code until
a product is ”ready” (or money or time
runs out). Work is in random order.
Corresponds with no plan! (Hacking!)

## Slide 13: Advantages
No administrative overhead
Signs of progress (code) early.
Low expertise, anyone can use it!
Useful for small “proof of concept” projects, e.g. as part of risk reduction.

## Slide 14: Disadvantages
Dangerous!
  No visibility/control
  No resource planning
  No deadlines
  Mistakes hard to detect/correct
2. Impossible for large projects,
communication breakdown, chaos.

## Slide 15: 6.6. Spiral Model
Since end-user requirements are hard to
obtain/define, it is natural to develop
software in an experimental way: e.g.
Build some software
See if it meets customer requirements
If no goto 1 else stop.

## Slide 16
This loop approach gives rise to structured iterative lifecycle models.
In 1988 Boehm developed the spiral
model as an iterative model which
includes risk analysis and risk
management.
Key idea: on each iteration identify and
solve the sub-problems with the highest
risk.

## Slide 17
Cumulative cost
Evaluate alternatives,
Identify & resolve risks
Develop & verify
next-level product
Plan next phase
Determine objectives,
alternatives & constraints
Review &
commitment
Prototypes
P1
P2
P3
Operational
Prototype
Start
End
Requirements
plan
Development
plan
Integration &
Test plan
Requirements
validation
Design,
Validation
& Verification
Detailed design
Coding
Unit & Integration
Testing
Acceptance
Testing
Concept
Of Operation

## Slide 18
Each cycle follows a waterfall model by:
Determining objectives
Specifying constraints
Generating alternatives
Identifying risks
Resolving risks
Developing next-level product
Planning next cycle

## Slide 19: Advantages
Realism: the model accurately reflects the iterative nature of software development on projects with unclear requirements
Flexible: incoporates the advantages of the waterfall and rapid prototyping methods
Comprehensive model decreases risk
Good project visibility.

## Slide 20: Disadvantages
Needs technical expertise in risk analysis to really work
Model is poorly understood by non-technical management, hence not so widely used
Complicated model, needs competent professional management. High administrative overhead.

## Slide 21: 6.7. Rapid Prototyping
Key idea: Customers are non-technical and usually don’t know what they want/can have.
Rapid prototyping emphasises requirements analysis and validation,also called:
customer oriented development,
evolutionary prototyping

## Slide 22
Requirements Capture
Quick Design
Build Prototype
Customer Evaluation of
Prototype
Engineer Final
Product
The Rapid
Prototype Workflow
Iterate

## Slide 23: Advantages
Reduces risk of incorrect user requirements
Good where requirements are changing/uncommitted
Regular visible progress aids management
Supports early product marketing

## Slide 24: Disadvantages I
An unstable/badly implemented prototype often becomes the final product.
Requires extensive customer collaboration
  Costs customers money
  Needs committed customers
  Difficult to finish if customer withdraws
  May be too customer specific, no broad market

## Slide 25: Disadvantages II
3. Difficult to know how long project will last
4. Easy to fall back into code-and-fix without proper requirements analysis, design, customer evaluation and feedback.

## Slide 26: 6.10. Unified Process (UP)
Lifetime of a software product in cycles:
Birth, childhood, adulthood, old-age, death.
Product maturity stages
Each cycle has phases, culiminating in a new release (c.f. Spiral model)

## Slide 27
Inception
Elaboration
Construction
Transition
UP Lifecycle – single phase workflow
(drawn as a UML Statechart!)

## Slide 28
Inception – identify core use cases, and use to make architecture and design tradeoffs. Estimate and schedule project from derived knowledge.
Elaboration – capture detailed user requirements. Make detailed design, decide on build vs. buy.
Construction – components are bought or built, and integrated.
Transition – release a mature version that satisfies acceptance criteria.

## Slide 29
Unified Process
Software Lifecycle
Cycle
Phase
Iteration
Artifact
Workflow
Management
Environment
Requirements
Design
Implementation
Assessment
Deployment
*
*
Inception
Elaboration
Construction
Transition
*
*
4
Product
releases

## Slide 30
Use Case Model
Analysis Model
Design Model
Deployment Model
Implementation Model
Test Model
specified by
realised by
deployed by
implemented by
verified by
All models are interdepedent
but this only shown for use
case model
UML class diagram!

## Slide 31: 6.11. COTS
COTS =
Commercial Off-The-Shelf software
Engineer together a solution from existing commercial software packages using minimal software ”glue”.
E.g. using databases, spread sheets, word proccessors, graphics software, web browsers, etc.

## Slide 32
Advantages
Fast, cheap solution
May give all the basic functionality
Well defined project, easy to run
Disadvantages
Limited functionality
Licensing problems, freeware, shareware, etc.
License fees, maintainance fees, upgrade compatibility problems